Advent Episode D1 — Advent of Invitation: Family Front Doors Toolkit

## Purpose

Design two simple, joyful first steps (Breakfast with Santa + Ask Anything Coffee) that meet real spiritual hunger and set up January momentum.

## Timeline (Suggested)

☐ T-8 weeks: Confirm dates/rooms, owners, and budget.

☐ T-7 weeks: Publish save-the-date; order supplies; recruit storytellers (2×90-sec).

☐ T-6 weeks: Launch RSVP landing page (HELLO QR points here).

☐ T-3 week: Volunteer huddle + signage print; test HELLO auto-reply & 24-hour callback flow.

☐ Event week: Run 60-minute volunteer huddle; execute; collect HELLO names.

☐ 48 hours after: 24-hour callbacks complete; send thank-you + January invites.

## Owners & Zones

| Zone / Piece | Owner | Backup |
| --- | --- | --- |
| HELLO table + 24-hour callbacks | Hospitality Lead | Comms Associate |
| Greeters & Wayfinding | Hospitality Captain | Usher Lead |
| Storytellers (2×90 sec) & Mic | Program Host | Assistant Host |
| Photo Spot + Family Blessing Cards | Family Ministry | Volunteer Photographer |
| Coffee/Donuts / Breakfast Logistics | Events Lead | Kitchen Team |

## Breakfast with Santa — Run of Show (60–75 min)

☐ Welcome (2 min): 'Santa points to Jesus' framing + how morning flows.

☐ Nativity Moment (5 min): Short reading + carol; optional kid blessing.

☐ Photos & Crafts (30–45 min): Photo booth, coloring; volunteers mingle.

☐ HELLO Invitation (20s): 'Scan HELLO; a real person texts you once within 24 hours.'

☐ Next Steps Table: Christmas Mass times; January 'Come & See + Fish Fry/Bingo' RSVP; Hallow Pray40 card.

### Mic Script — Welcome (reader-ready)

“Good morning! Today we have fun—and we remember Santa points us to Jesus. If you’re new or returning, you’re so welcome. Scan HELLO and we’ll text you once with a gentle next step.”

## Ask Anything Coffee after Mass (20–25 min)

☐ Set 3–4 round tables near narthex; 'No question too basic' tent cards.

☐ Two 90-sec witness stories; then open Q&A with a pastor at each table.

☐ Capture HELLO names at tables; schedule coffee meetups for next Sunday.

## Signage & Card Copy (paste-ready)

| Sign | Copy |
| --- | --- |
| HELLO Sign | New or returning? You’re so welcome. Scan HELLO. A real person will text you once within 24 hours. |
| Pew/Narthex Card | Curious this Advent? We’d love to pray with you. Scan HELLO for one gentle next step. No pressure. |

## Follow-Up Templates

### Auto-Reply (HELLO)

“Thanks for saying hello to Saint….—honored you’re here. Anything we can pray for today? We’re hosting a friendly ‘Come & See + Fish Fry/Bingo’ night in January—want me to save you a seat?”

### 24-Hour Callback (60s)

“Hi ___, I’m ___ from Saint …. Thanks for sharing your name. Is there anything we can pray for? A simple next step: coffee next Sunday or our January Come & See night—happy to meet you at HELLO.”